## Private Label SOP Final 2024
[5 empty] | PRODUCT SOURCING, DEVELOPMENT & LAUNCH PREP | [39 empty] | GO LIVE! |  |  |  |  | MONTH ONE | [14 empty] | MONTH TWO
| PRIVATE LABEL STAGE | SOP AND/OR REFERENCE LINK | DUE DATE | STATUS | WEEK -1 |  |  |  |  | WEEK -2 |  |  |  |  | WEEK -3 |  |  |  |  | WEEK -4 |  |  |  |  | WEEK -5 |  |  |  |  | WEEK -6 |  |  |  |  | WEEK -7 |  |  |  |  | WEEK -8 |  |  |  |  | LAUNCH WEEK |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8
| PRODUCT DISCOVERY & AI DESIGN |  | DUE DATE | STATUS | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1.1 | Define your specific and measurable goals. | SOP for Goal Setting and Resource Evaluation
1.2 | Determine budget requirements, including assessing available capital. | SOP for Goal Setting and Resource Evaluation
1.3 | Evaluate available time and human resources for the project. | SOP for Goal Setting and Resource Evaluation
1.4 | Assess your risk profile, considering financial stability, experience, and market knowledge. | SOP for Product Risk Assessment
1.5 | Identify unique value propositions like niche expertise and supplier relationships. | SOP for Product Risk Assessment
1.6 | Evaluate existing product sales to identify complementary products. | SOP for Product Risk Assessment
1.7 | Outline a preliminary timeline with key milestones for each phase. | Private Label SOP Project Timeline
1.8 | Research potential products via Jungle Scout or other methods | SOP for Researching Potential Products
1.9 | Run Data Dive to analyze opportunity and competition | Validate - Data Dive Office Hours
1.1 | Confirm consistent demand via Etsy, Pinterest, Google trends | SOP for Validating Demand and Differentiating Products
1.11 | Identify product differentiation from competitors. | SOP for Validating Demand and Differentiating Products
1.12 | Overview of MidJourney | SOP for Product Design with MidJourney
1.13 | Using MidJourney to generate designs | SOP for Product Design with MidJourney
| PRODUCT VALIDATION |  | DUE DATE | STATUS
2.1 | Research suppliers on 1688 or Alibaba for baseline pricing estimates | How To Find Best Products in China
2.2 | Calculate all relevant fees and confirm the product category. | Amazon Revenue Calculator
2.3 | Conducted feasibility analysis, including order planning and cost calculation. | SOP for Cash Flow and Profitability Analysis
2.4 | Ensure the selling price is at least 4-5 times the landed cost to maintain profit margins. | SOP for Cash Flow and Profitability Analysis
2.5 | Use profit calculators to determine ROI. | Data Dive Profit Calculator
2.6 | Review the distribution of keyword search volume and traffic. | SOP for Product Validation using Data Dive Scorecard
2.7 | Assess product lifecycle and ROI | SOP for Product Validation using Data Dive Scorecard
2.8 | Evaluate potential savings on packaging and fulfilment costs. | SOP for Product Validation using Data Dive Scorecard
2.9 | Determine the feasibility of obtaining utility or design patents. | SOP for Product Validation using Data Dive Scorecard
2.1 | Assess competition based on price, reviews and content quality. | SOP for Product Validation using Data Dive Scorecard
2.11 | Monitor market trends and seasonality impacts. | SOP for Product Validation using Data Dive Scorecard
2.12 | Analyze variations and major brand presence. | SOP for Product Validation using Data Dive Scorecard
2.13 | Run the Product Validation Scorecard and decide if the product is worth selling on Amazon. | Data Dive Product Scorecard
| LEGAL, SAFETY & COMPLIANCE |  | DUE DATE | STATUS
3.1 | Conduct a thorough trademark search. | SOP for Conducting a Thorough Trademark and Patent Search
3.2 | Ensure your product does not infringe on existing patents. | USPTO Trademark Search and Google Patents
3.3 | Comply with all relevant product safety standards and obtain certifications. | SOP for Ensuring Product Safety and Compliance, (CPSC, SGS, CE Marking
3.4 | Comply with environmental regulations. | RoHS Compliance and WEEE Compliance
3.5 | Comply with California's Proposition 65 regulations. | California Proposition 65
3.6 | Follow the import/export regulations for all countries you sell in | International Trade Administration
3.7 | Review and follow Amazon’s guidelines for product listings, reviews, and fulfilment. | Amazon Seller Central
3.8 | Apply for copyright registration for your original content through the U.S. Copyright Office. | U.S. Copyright Office
3.9 | Ensure proper collection and remittance of sales taxes. | Sales Tax Handbook
| PRODUCT SOURCING, PROCUREMENT, QC |  | DUE DATE | STATUS
4.1 | Finalize product specs & write product brief | SOP for Sourcing and Supplier Communication
4.2 | Research suppliers and create a shortlist | SOP for Sourcing and Supplier Communication
4.3 | Obtain NNN or non-disclosure agreement with company chop from shortlisted suppliers | SOP for Sourcing and Supplier Communication
4.4 | Send a brief and submit RFQ to shortlisted suppliers | SOP for RFQ Submission and Supplier Analysis
4.5 | Add responses to supplier summary template and analyze data | SOP for RFQ Submission and Supplier Analysis
4.6 | Select top 3 suppliers to provide samples and use a consolidator to consolidate samples | SOP for RFQ Submission and Supplier Analysis
4.7 | Order and review samples, then pick your top supplier | SOP for Sample Review and Supplier Selection
4.8 | Finalize product pricing & profitability from the supplier shortlist | SOP for Sample Review and Supplier Selection
4.9 | Order golden/final samples from the factory (Optional) | SOP for Final Sample Approval and Purchase Order Process
4.1 | Make a decision on whether to move forward with PO | SOP for Final Sample Approval and Purchase Order Process
4.11 | Send purchase order & pay deposit to proceed with production | SOP for Final Sample Approval and Purchase Order Process
4.12 | Request photos from the supplier for periodical checkpoints through production and request final sample for product photography | SOP for Final Sample Approval and Purchase Order Process
4.13 | Book inspection and testing | SOP for Booking Inspection and Testing
| LOGISTICS |  | DUE DATE | STATUS
5.1 | Identify Key Logistics Metrics: weight, volume, dimension and tiers | Key Logistics Metrics Template
5.2 | Confirm the total gross weight and dimension of the master carton | Master Carton Requirements
5.3 | Review shipping label requirements | Shipping Label Requirements
5.4 | Confirm shipping marks: fragile, keep dry, this way up, handle with care | Shipping Marks
5.5 | Obtain & Compare quotes from Freight Forwarders and 3PLs if required | SOP for Freight Forwarder and 3PL Selection
5.6 | Send purchase order to freight forwarder & pay deposit | SOP for Freight Forwarder and 3PL Selection
5.7 | Create a shipping plan in Seller Central | Ship products to Amazon
5.8 | Review product inspection report & approve shipping | SOP for Freight Forwarder and 3PL Selection
| PHOTOGRAPHY, DESIGN & PACKAGING |  | DUE DATE | STATUS
6.1 | Review Amazon product image requirements | Amazon Product Images Requirements & Best Practices
6.2 | Research and brainstorm highly convertible image ideas | SOP for Creating High-Converting Product Images
6.3 | Create a detailed photography brief | Photography Brief
6.4 | Inquire from different photographers | Sample Email to Photographer
6.5 | Select a photographer/designer and proceed with image creation | Selecting a Photographer/Designer and Proceeding with Image Creation
6.6 | Start the Photography and Design Process | Selecting a Photographer/Designer and Proceeding with Image Creation
6.7 | Approve / Finalize images | Selecting a Photographer/Designer and Proceeding with Image Creation
6.8 | Run a split testing campaign on graphics, images, designs, etc | Split Testing Campaign
6.9 | Create A+ content and images | A+ Content Creation
6.10 | Work with supplier for packaging - requesting options, including samples | Packaging and prep requirements
6.11 | Review packaging options with samples & make a final decision for a purchase order. | Packaging and prep requirements
6.12 | Reconfirm Amazon FBA and monthly storage fees with final product size/dimensions. | Amazon Revenue Calculator
6.13 | Work with the designer to create inserts | Product insert compliance
6.14 | Approve insert design and send final artwork for printing | SOP for Product Inserts
6.15 | Obtain quotes for insert printing (factory or printers) | SOP for Product Inserts
6.16 | Determine which barcodes are required | FBA product barcode requirements
6.17 | Apply for GTIN exemption or purchase GS1 barcodes | Find your product ID (GTIN)
6.18 | Submit critical information for packaging requirements with the supplier [including barcodes and label requirements] | SOP for Packaging Requirements and Compliance
6.19 | Ensure packaging, barcodes, and labelling are approved & correct during production before shipment. | SOP for Packaging Requirements and Compliance
| BRAND |  | DUE DATE | STATUS
7.1 | Create an Amazon Seller Central Account | Amazon Seller Central Account Setup
7.2 | Apply for brand registry | Brand Registry Application
7.3 | Register brand name & logo with Amazon IP Accelerator | Brand Registration with IP Accelerator
7.4 | (Optional) obtain a domain for the website | Optional
7.5 | (Optional) obtain social media pages for the brand | Optional
7.6 | (Optional) Start social media campaigns to increase engagement and drive traffic for launch prep. | Outside Traffic & Marketing Module
| LISTING & PRE-LAUNCH PREP |  | DUE DATE | STATUS
8.1 | Review product listing guide. | Product Listing Style Guide
8.2 | Cross-check 'do not use' words | Prohibited Keywords List
8.3 | Refresh Data Dive and prep it for listing copywriting | Data Dive Listing Builder
8.4 | Create a suppressed product listing in Seller Central (Preserve the Honeymoon) | SOP for Creating a Suppressed Product Listing
8.5 | Identify the most relevant keywords to target for your product. | Data Dive Master Keyword List (MKL)
8.6 | Create a compelling and keyword-optimized product listing. | Data Dive Listing Builder
8.7 | Upload listing images. | Listing Images and A+ Content
8.8 | Set up a tool to track your keyword rankings. | Data Dive Rank Radar
8.9 | Set reminders for operational checks (alerts, BSR, analytics, seller feedback, inventory) | JungleScout Alerts
9 | Set reminders for the PPC optimization schedule | Optional
9.1 | Set up automated follow-up email review requests | Amazon Request a Review Tool or JungleScout
| LAUNCH DAY |  | DUE DATE | STATUS
10.1 | Change suppressed listing dates to today. | SOP for Launch Day
10.2 | Check the listing content to see if everything is in order. | SOP for Launch Day
10.3 | Activate PPC campaigns. Start with manual campaigns. | SOP for Launch Day
10.4 | Drive traffic from external sources like social media, email lists, or influencer partnerships. | Outside Traffic & Marketing Module
10.5 | Use promotions or discounts to attract initial buyers. | Deals, Coupons and Prime Exclusive Discount
10.6 | Enroll on Vine Program | Amazon Vine
| POST-LAUNCH |  | DUE DATE | STATUS
10.1 | Track key metrics like CTR, conversion rate, and keyword ranking. | PPC Live Sessions and Rank Radar
10.2 | Test images, bullet points, and descriptions to see what works best. | SOP for Amazon Listing Optimization
10.3 | Adjust prices and offer coupons to attract more buyers. | SOP for Amazon Listing Optimization
10.4 | Ensure Amazon indexes all important keywords | SOP for Ensuring Amazon Indexes All Important Keywords
10.5 | Regularly review and adjust PPC campaigns. | SOP for PPC Launch and Optimization
10.6 | Encourage early buyers to leave reviews to build social proof. | Optional
10.7 | Ensure you have enough stock to meet demand and avoid running out of stock | SOP for Inventory Management
10.8 | Conduct weekly and monthly deep dives to track progress and identify areas for improvement. | How do I schedule and shut off a scheduled Auto Dive?